RUSSIA NUCLEAR DATA CENTER - RNDC

Alias: CENTR JADERNYKH DANNYKH - CJD

Institute for Physics and Power Engineering - IPPE

Bondarenko Sq., 1, Obninsk 249033, Kaluga Region, RUSSIA

Telephone:	+7 (48439)98779 (M.Mikhailiukova)

Fax:			+7 (48439)68225

Web-site: 	www.ippe.ru/podr/cjd

MEMO 4C-4/208

| Date: | 21 April 2014 |
| --- | --- |
| To: | Distribution |
| From: | M.Mikhailiukova |
| Subject: | CJD Progress Report for NRDC2014 |

CJD PROGRESS REPORT

NRDC Technical Meeting

(06 - 09 May 2014, Congress Center Smolenice, Slovakia)

Russian Nuclear Data Center

(CJD, IPPE, Obninsk, Russian Federation)

Introduction

During the time passed after the previous NRDC2013 meeting the current work concerning EXFOR compilation and fulfillment of NRDC2013 Conclusions and Actions was continued. Large part of activity was related to the nuclear data evaluation.

1. Staff

At present moment the CJD center is in reorganization process. It’s planned that CJD will be a laboratory within the theoretical division of “Department for perspective researches“ in the State Scientific Centre of the Russian Federation – Institute for Physics and Power Engineering named after A.I. Leypunsky – SSC RF – IPPE.

2. EXFOR activity.

After the NRDC2013 Meeting:

- Exfor Transes 4160-4162 were transmitted as final;

- Exfor Trans 4163 was transmitted as preliminary.

EXFOR compilation statistics – area 4

| Trans | Date/status | Entries Total | Entries New | Entries Revised | Subents Total | Subents New in old+in new | Subents Revised (cor.+NOSUBENT) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4160 | 21-06-2013/final | 24 | 2 | 22 | 235 | 0+6=6 | 229 |
| 4161 | 24-12-2013/final | 47 | 3 | 44 | 490 | 12+13=25 | 455+10=465 |
| 4162 | 14-02-2014/final | 50 | 8 | 42 | 272 | 28+35=63 | 202+7=209 |
| Final |  | 121 | 13 | 108 | 997 | 94 | 903 |
| 4163 | 17-04-2014/prelim. | 33 | 3 | 30 | 232 | 68+18=86 | 139+7=146 |
| Total |  | 154 | 16 | 138 | 1229 | 108+72=180 | 1025+24=1049 |

-The efforts were continued to get numerical data from authors.

Good cooperation was established with Russian authors:

V.Shorin, V.Piksaykin, V.Khryachkov (4RUSFEI);

O. Shcherbakov, A.Vorobiev, I.Guseva (4RUSLIN);

V.Dement’ev (4RUSKUR);

A.Filatenkov (STC "Yafi" near 4RUSRI );

Sh.Zeynalov, D.Testov (4ZZZDUB).

- Neutron induced data Transes were checked and comments were sent:

10 for area 1,

2 for area 2,

5 for area 3.

- Russian journals YF, AE, IZV, PTE, ZET, ZEP, FCY, FCY/L are scanned and information for CoCoS is sent to NDS in coordination with V.Semkova.

- Four memos (# 204-207) were prepared and sent for NRDC community for discussion:

Reply to draft of NRDC2013 Conclusion C6

New codes for dictionary 36/236- PR/TER,NU/DA,N+FF, PR,NU/DA/DE,N+FF/N

New codes for dictionary 36/236- SEC,KE

Free Entries numbers in EXFOR.

3. NRDC2013 Actions.

CJD is responsible for NRDC-2013 Actions: 1, 6, 7, 9, 10, 11, 24, 36, 39, 44, 45, 46, 53, 54, 59, 65, 73, 76.

A1 – All the articles registered ( 21.04.2014 ) in CoCoS were compiled.

A6 – All very urgent and urgent corrections were made ( 21.04.2014, last prelim.trans 4163). The normal corrections will be continued.

A7 - Anatoly Andreev was nominated from the CJD for participation in the EXFOR working group coordinated by V.Zerkin.

A9 – No questionnaire was received, so no feedback was sent.

A10 – Feedback on NRDC paper for ND2013 was sent.

A11 – Comments on the Network document were not sent.

A24 – Feedback on new covariance format was sent by V.Pronyaev.

A36 – Checking was started but has not finished yet. Some new data were added in EXFOR.

A39 – Finished in prelim.4163.

A44, 45, 46 – Not all the English translations of AE, YF, YK, IZV were added. The Actions will be continued.

In corrected Entries – complex corrections are done in all SUBENTs and found misprints, mistakes, duplications (not mentioned in NDS error list) are corrected.

Added for AE -15, YF – 27, YK – 25, IZV- 4, FCY -1, ZEP -2, ZET – 2, PTE – 1, KIEV conf. – 1, NIIAR- -1, ICD- - 1 - total 80 .

A53 –Addition of data according to NODATA list will be continued

A54 – Feedback on WP2013-25,-26 was not sent

A59 – Usually feedback on CHEX is sent in comments of transes.

A65 – X+ format is not used in compilation, but a comment from author (V.Khryachkov) was sent and discussed.

A73 – No feedback on GSYS was sent.

A76 – Feedback on Sarov’s digitizer was sent.

4. Computer and software matters. WEB-site service.

- New versions of Sarov’s digitizer and EXFOR dictionaries were copied and used in compilation.

- Tool of web-service for compilers developed by V.Zerkin, Janis Trans Checker (NEA DB) and CHEX are used to check transes.

- The information from web-site of users’ feedback is helpful for correction of the old Entries.

- EXFOR status compilation web-page CoCoS is used for information about the articles registered for the compilation.

- CJD web-site (Russian/English) is still under reconstruction as also IPPE web-site.

5. Nuclear data evaluation activity.

Nuclear data evaluation process and compilation of nuclear data files for the BROND-3 project were continued in CJD. Testing and benchmarking of BROND-3 preliminary version is still going on, additions and updating are planned to be done. Finalizing is planned at the end of 2014.

6. Journal YK.

The journal “Yadernye Konstanty”-2011-2012, issue 1-2 is the last published one. The next issue 2013-2014 is planned to be prepared at 2014 year, if financial support will be obtained for this publication.

YK 1999 – 2007 issues are available to read from the old CJD web-site http://www.ippe.obninsk.ru/podr/cjd/ . Some translations are available at NDS web-site.

7. Acknowledgments.

Great thanks to:

- Naohiko Otsuka and Emmeric Dupont for their comments of Transes and productive discussions;

- Valentina Semkova for her collaboration concerning CoCoS;

- Viktor Zerkin for his very helpful comments about computer codes and tools for EXFOR;

- L.Vrapsenjak and A.Oechs for assistance;

- experimentalists for sent authors’ data and very useful explanations;

- EXFOR data base users for their feedback and comments, which are important for EXFOR improvement.